CLSTR.IN

CAMPUS CAPTAIN

90-DAY WEEKLY EXECUTION PLAN

July 1 – September 30, 2026

| 1k–5k Target, scaled by college size | 39 Reels — 3/week for 13 weeks | 8+ Clubs onboarded and active |
| --- | --- | --- |

# The Mission, In Numbers

This is the execution layer for your college. Everything in the Ambassador Guidebook — your role, your Domain Team, your KPIs — now runs on a fixed 13-week calendar with a single target: 5,000 verified users from your college by September 30, 2026, backed by a 3-reels-per-week content engine and full club activation.

| TRACK | TARGET | CADENCE | OWNER |
| --- | --- | --- | --- |
| Verified sign-ups | 5,000 by Week 13 | Weekly target, see table | Growth & Outreach Lead |
| Instagram Reels | 3 per week, every week | 1 meme + 1 culture/story + 1 conversation/branding | Community Lead + You |
| Club activation | 8+ clubs posting live | ~1 new club onboarded every week, Wk 3–9 | Clubs & Events Lead |
| Weekly reporting | 13/13 weeks submitted | Every Monday, 10am | You (Campus Captain) |

# The 3-Reels-a-Week System

Every week, three reels go up from your college's presence — no exceptions, no "nothing happened this week." The formula below repeats every week so your Community Lead can execute it without waiting on you.

100% HUMAN-SHOT. NO AI-GENERATED CONTENT AT THE CAMPUS LEVEL. These reels are filmed by you, your Domain Leads, and Foot Soldiers — on your own phones, with real students on camera. That authenticity is the entire point: it's what makes a reel feel like it came from campus, not from a brand account, and it's what earns the organic share that gets it collab-worthy. Any AI-generated reel library the main Clstr account runs is a separate, central system — it is not a substitute for your own content.

The weekly formula

•  Reel 1 — MEME. Trending audio or format, made campus-specific. This is your reach engine — highest share rate, lowest production effort.

•  Reel 2 — CAMPUS CULTURE or STUDENT STORY. Real students, real moments (canteen, hostel, events, wins). This builds "is this really my campus?" trust.

•  Reel 3 — STUDENT CONVERSATION or BRANDING. Vox-pops, testimonials, or a direct feature moment (a club president posting live, a milestone recap).

Who shoots it

•  Community Lead owns the weekly reel calendar and is the default shooter/editor.

•  Foot Soldiers help film on the day — extra hands for crowd shots, multiple angles, candid reactions.

•  You (Campus Captain) appear on camera for branding/milestone reels — face-to-camera builds trust faster than a voiceover.

•  Students featured in culture/story reels are filmed spontaneously with their consent — no scripts, no retakes for polish. Rough and real beats polished and generic.

•  Editing stays light — trim, trending audio, text overlay, end card. A phone editing app (CapCut/InShot) is enough. Do not over-produce; an overly polished reel reads as an ad and gets scrolled past.

Non-negotiable rules for every reel

•  Tag @clstr.in and request the Instagram Collab feature on every post — this is what pushes your college's content onto the main Clstr account's reach, not just your own followers.

•  Use #ClstrOn[YourCollege] on every reel for trackability.

•  Brand constants: Space Grotesk Bold text overlays, lime #CCFF00 on black #000000 for any text card, end card with the Clstr end-screen every time.

•  Would students actually send this to their college WhatsApp group? If the answer is no, don't post it — this is the only filter that matters.

•  Raw footage goes to the Clstr content team the same day it's shot, even if you've already posted — the main account may reuse it.

# Week-by-Week Master Plan

The onboarding curve is intentionally not flat — it ramps through fresher season and Independence Day (Weeks 6–10), then tapers as mid-semester exams hit (Weeks 11–13). Hit the weekly percentage, not just the cumulative one; a missed week compounds. Targets are shown as % of your college's tier target — see "Scaling Your Target by College Size" for your exact numbers. The small grey figures use the 5,000-user Tier 1 college as a worked example only.

| WEEK | ONBOARDING (% of your target) | 3 REELS THIS WEEK | CLUB & DOMAIN FOCUS | MILESTONE |
| --- | --- | --- | --- | --- |
| WK 1 Jul 1 – Jul 7 SETUP | 2% of target cum. 2% (T1 ex.: +100, cum. 100) | • Branding — "Meet your Campus Captain" intro reel. Face-to-camera, energetic, ends on brand end card. • Campus Culture — "POV: first day back on campus" walk-through, lime text overlays. • Meme — relatable fresher/reopening-week meme using trending audio. | Club: Map every active club + committee. Shortlist 3 to approach in Week 2. No club onboarding yet — foundation week. Domain: Recruit all 4 Domain Leads. Ambassador WhatsApp group live. Assign roles. Set weekly 20-min team call slot. | Team fully formed + first 3 reels live, all tagged/collab-requested with @clstr.in. |
| WK 2 Jul 8 – Jul 14 MAPPING | 3% of target cum. 5% (T1 ex.: +150, cum. 250) | • Meme — "things only [college] students understand" (campus-specific inside joke). • Campus Culture — canteen/hostel/library POV reel, lime brand overlay on captions. • Student Conversation — quick vox-pop: "what do you wish your college app did?" 3-4 student clips. | Club: Pitch 3–4 clubs directly. Get first verbal yes. Identify 10 high-influence students (club leads, seniors, sports captains). Domain: Growth Lead starts QR poster placement (5 high-traffic spots). Community Lead builds 10–15 person Campus Creators WhatsApp group. First WhatsApp broadcast sent. | 250 users cumulative. First club verbal commitment secured. |
| WK 3 Jul 15 – Jul 21 FIRST ACTIVATION | 5% of target cum. 10% (T1 ex.: +250, cum. 500) | • Student Story — feature the club president posting their first event live on Clstr (real, unscripted). • Meme — hostel/canteen/exam-fear meme, trending format. • Campus Culture — "day in the life of a fresher at [college]" story reel. | Club: Onboard 2 clubs LIVE — sit with each president and post their first event together. Never leave it as a verbal yes. Domain: CollabHub Lead creates first live Team-Up post for a real ongoing project. QR posters checked/refreshed. | ★ MILESTONE 1 — 500 users + 2 active clubs. Merch reward unlocked. |
| WK 4 Jul 22 – Jul 28 GROWTH SPRINT | 6% of target cum. 16% (T1 ex.: +300, cum. 800) | • Branding — recap reel of the on-campus info session (energy, crowd, sign-up moment). • Meme — relatable academic-life meme tied to trending audio. • Student Story — first testimonial reel: one real student on why they use Clstr. | Club: Onboard 3rd club. Push RSVP for any club event this week — target 60%+ attendance of RSVPs. Domain: Growth Lead runs first on-campus info session. Personally walk first 10 sign-ups through the flow (5x conversion vs QR-only). | Week 4 report submitted. First testimonial live on feed + reel. |
| WK 5 Jul 29 – Aug 4 ACTIVATION LOOPS | 7% of target cum. 23% (T1 ex.: +350, cum. 1,150) | • Student Conversation — alumni/senior spotlight: "what I wish I knew as a fresher." • Meme — mid-July academic grind meme. • Campus Culture — feed-content prompt reel encouraging Campus Creators to post their own wins. | Club: Onboard 4th club. Begin TPO/placement office conversation using the pitch deck — sell outcome, not app. Domain: Placement Lead pushes mentorship sign-ups. Community Lead re-seeds feed if it's gone quiet — one active post resets momentum. | 1,150 users cumulative. TPO conversation opened. |
| WK 6 Aug 5 – Aug 11 MOMENTUM BUILD | 8% of target cum. 31% (T1 ex.: +400, cum. 1,550) | • Meme — pre-Independence Day patriotic-but-funny meme format. • Student Conversation — "3 things I'd change about campus life" vox-pop. • Campus Culture — club-event RSVP push reel for an upcoming Aug 15 event. | Club: 5th club active. Check RSVP-to-attendance rate on last event — fix drop-off if under 60%. Domain: Domain Lead output review — 100% task completion check. Replace any lead inactive since Week 4. | 1,550 users cumulative. All 4 Domain Leads active and delivering. |
| WK 7 Aug 12 – Aug 18 INDEPENDENCE DAY PUSH | 9% of target cum. 40% (T1 ex.: +450, cum. 2,000) | • Branding — Aug 15 campus celebration reel, collab-posted for max reach that week. • Meme — festival/holiday-week meme. • Student Story — "campus voices" — students share one campus memory on camera. | Club: 6th club active. Use Aug 15 campus energy for a joint club + Clstr activity if possible. Domain: Full team sync call. Escalate any blocker older than 24 hours to Ambassador PM — do not sit on it. | ★ MILESTONE 2 — 2,000 users + 4 active clubs. |
| WK 8 Aug 19 – Aug 25 SCALE WEEK | 10% of target cum. 50% (T1 ex.: +500, cum. 2,500) | • Campus Culture — fresher's day / cultural fest tie-in reel (peak seasonal relevance). • Meme — fest-season meme, high shareability format. • Student Story — one more real testimonial, different domain (e.g. CollabHub or mentorship user). | Club: 7th club active. Cross-promote fest content with clubs running fresher's day events. Domain: Growth Lead runs 2nd on-campus info session. Personally onboard 10 more students live. | 2,500 users cumulative — halfway point of the 5,000 target. |
| WK 9 Aug 26 – Sep 1 DEEPEN ENGAGEMENT | 11% of target cum. 61% (T1 ex.: +550, cum. 3,050) | • Meme — trending audio meme, campus-specific. • Student Conversation — CollabHub team-up in action: two students who matched building something. • Campus Culture — alumni engagement reel via TPO/mentorship connection. | Club: 8th club active — approaching full domain coverage. Confirm all clubs have posted in last 7 days. Domain: Feed activity check — target 50+ actions/week. Community Lead re-seeds if below target. | 3,050 users cumulative. 8 clubs active. |
| WK 10 Sep 2 – Sep 8 PEAK SPRINT | 12% of target cum. 73% (T1 ex.: +600, cum. 3,650) | • Campus Culture — Ganesh Chaturthi / festival-season reel tied to campus celebrations. • Meme — highest-effort meme of the sprint, aim for widest organic reach. • Branding — placement/internship reel if TPO listing has landed by now. | Club: Sustain all 8 clubs. Push one more high-visibility event with strong RSVP push. Domain: Highest single-week onboarding target — all-hands push. Every Domain Lead personally walks 5+ sign-ups. | 3,650 users cumulative. Peak weekly onboarding number of the sprint. |
| WK 11 Sep 9 – Sep 15 PRE-EXAM PUSH | 11% of target cum. 84% (T1 ex.: +550, cum. 4,200) | • Meme — mid-sem study-stress meme, high relatability during exam prep. • Student Conversation — "how Clstr helped me this semester" quick clips. • Campus Culture — study-group / library culture reel. | Club: Sustain club activity through exam season — shift event cadence lighter, keep feed alive. Domain: Mid-point Domain Lead performance review. Flag anyone drifting before exams fully hit. | 4,200 users cumulative. Team holding steady into exam season. |
| WK 12 Sep 16 – Sep 22 FINAL STRETCH | 10% of target cum. 94% (T1 ex.: +500, cum. 4,700) | • Meme — end-of-sprint high-energy meme. • Student Story — campus wins compilation reel (best moments from the last 11 weeks). • Branding — case-study style testimonial, positioned for repost on main Clstr account. | Club: Confirm RSVP-to-attendance rate is holding at 60%+ across all clubs. Domain: Begin drafting the 90-day final report. Identify next-semester bench / successor candidates. | 4,700 users cumulative. Final push week begins. |
| WK 13 Sep 23 – Sep 30 MILESTONE CLOSE-OUT | 6% of target cum. 100% (T1 ex.: +300, cum. 5,000) | • Branding — "3 months in numbers" recap reel — built for a collab feature on the main Clstr account. • Meme — thank-you/community meme closing the sprint on a high note. • Student Story — next-chapter teaser reel building anticipation for the Vizag community track. | Club: Lock in all active clubs for continuation next semester. No club left without a next scheduled post. Domain: Submit full 90-day report. Hand off bench candidates. Celebrate the team publicly. | ★ FINAL MILESTONE — 5,000 verified users. Vizag community gate unlocked for this campus. |

# Scaling Your Target by College Size

5,000 is the flagship number for a mega-campus — it is not a one-size-fits-all target. Every college in the 8-campus sequence gets a target sized to its actual student population, using the same 30–35% activation logic from the Ambassador Guidebook ("at 10,000 students, 2,000 is 20% — very achievable"), pushed further here because this sprint has a dedicated reel engine behind it.

| TIER | COLLEGE SIZE | 90-DAY TARGET | NOTES |
| --- | --- | --- | --- |
| Tier 1 — Mega | 15,000+ students | 5,000 | e.g. VIT Vellore, KL University (confirmed 15k–30k+ range) |
| Tier 2 — Large | 8,000 – 15,000 students | 3,000 | e.g. GITAM, Andhra University — verify with each CA |
| Tier 3 — Mid | 4,000 – 8,000 students | 2,000 | e.g. ANITS, GVPCE+MVGR, SRKREC+SASTRA — verify with each CA |
| Tier 4 — Small | Under 4,000 students | 1,000 | e.g. Raghu Engineering College — verify with each CA |

Confirm each college's actual enrolled student count with its Campus Captain in Week 1 before locking the tier — these examples are working estimates, not verified figures.

Weekly cumulative target, by tier

Same 13-week ramp shape for every college (slow start → fresher-season/Independence-Day peak in Weeks 7–10 → exam taper) — only the scale changes. Find your tier's column and use those numbers in your Monday report.

| WEEK | Tier 1 (5,000) | Tier 2 (3,000) | Tier 3 (2,000) | Tier 4 (1,000) |
| --- | --- | --- | --- | --- |
| Wk 1 (2%) | 100 | 60 | 40 | 20 |
| Wk 2 (3%) | 250 | 150 | 100 | 50 |
| Wk 3 (5%) | 500 | 300 | 200 | 100 |
| Wk 4 (6%) | 800 | 480 | 320 | 160 |
| Wk 5 (7%) | 1,150 | 690 | 460 | 230 |
| Wk 6 (8%) | 1,550 | 930 | 620 | 310 |
| Wk 7 (9%) | 2,000 | 1,200 | 800 | 400 |
| Wk 8 (10%) | 2,500 | 1,500 | 1,000 | 500 |
| Wk 9 (11%) | 3,050 | 1,830 | 1,220 | 610 |
| Wk 10 (12%) | 3,650 | 2,190 | 1,460 | 730 |
| Wk 11 (11%) | 4,200 | 2,520 | 1,680 | 840 |
| Wk 12 (10%) | 4,700 | 2,820 | 1,880 | 940 |
| Wk 13 (6%) | 5,000 | 3,000 | 2,000 | 1,000 |

Reel cadence (3/week) and club activation cadence (~1 new club/week, Weeks 3–9, toward 8+ active) stay the same across every tier — content and club-onboarding effort doesn't scale down just because a campus is smaller.

# Milestone Ladder — Applies at Any Tier

Milestones trigger at the same % of YOUR college's tier target, not a fixed headcount — so a Tier 4 Campus Captain earns the same recognition path as a Tier 1 one, on numbers that are actually achievable for their campus size. This replaces the flat 2,000-user ladder in Guidebook v2.

| MILESTONE | % OF TARGET | T1 (5,000) | T2 (3,000) | T3 (2,000) | T4 (1,000) | REWARD |
| --- | --- | --- | --- | --- | --- | --- |
| M1 — Wk 3 | 10% | 500 | 300 | 200 | 100 | Merch (hoodie/cap) |
| M2 — Wk 7 | 40% | 2,000 | 1,200 | 800 | 400 | ₹500 voucher + shout-out |
| M3 — Wk 10 | 73% | 3,650 | 2,190 | 1,460 | 730 | Signed Campus Leader Certificate |
| M4 — Wk 13 | 100% | 5,000 | 3,000 | 2,000 | 1,000 | ₹2,000 cash + letter + community gate unlocked |
| M5 — End | Top rank | — | — | — | — | Fast-tracked core team / internship interview |

# Your Weekly Rhythm (every single week)

•  Monday: submit last week's report by 10am — sign-ups vs. target, reel performance, club status, one win, one blocker.

•  Monday/Tuesday: lock this week's 3 reel topics with Community Lead using the calendar above; shoot early in the week.

•  Daily: post/share one thing on the feed, check sign-up numbers, clear one pending task, respond to team blockers within 6 hours.

•  Weekly team call: 20 minutes with all 4 Domain Leads — review outputs, not every step. Non-negotiable.

•  Any blocker older than 24 hours goes to the Ambassador PM immediately — do not wait for the weekly call.